## Slide 1: Get A Grip on Safety
Case for Change

## Slide 2: What is "Get A Grip on safety"
The Get a Grip on Safety (or Get a Grip) Program is intended to be an "off the shelf" package of materials and resources to be used by organizations interested in eliminating slips, trips and fall incidents in their organization.
The Get a Grip program focuses on the following areas:
Transition Zones and Walkways
Boots and Grips
Access and Egress
Home Safety
Eyes on Path
Ladder Safety
The materials include:
Suggested activities and schedules
Program Procedures
Activity Sheets
Inspection Forms
Tools and Resources

## Slide 3: Current status?
    Creating a company-wide get a grip program presents a significant opportunity for injury prevention.
    Slip, trips and fall hazards, and the opportunity to correct them, are often overlooked.
    Slip, trip and fall related injuries are common and can lead to serious injury.
    The Get a Grip Program is aligned with Life Saving Rules and includes unsafe conditions as well.
    Slip, trip and fall hazards exist year-round (not a seasonal trend).

## Slide 4: How Significant Are slip, trip and fall injuries?
    According to WCB-Alberta in 2021,
    20.5 per cent of Alberta’s workplace lost-time claims are the result of falls:
    • 13.9 per cent – fall on same level
    • 6.0 per cent – fall to lower level
    • 0.6 per cent – other falls

## Slide 5: What Does our incident data indicate?
[Add your incident data and trends here:]

## Slide 6: Alignment with Life Saving Rules
The Get a Grip program is aligned with Energy Safety Canada’s 10 Life Saving Rules, which focus on safe behaviours, however it can also stand alone.
The program also includes aspects relating to unsafe conditions and unsafe acts.
Unsafe Behaviors
Unsafe Behaviors
Unsafe Conditions

## Slide 7: Energy Safety Canada’s 10 Life Saving Rules
NOTE: Nine rules were adopted from the International Association of Oil & Gas Producers (IOGP) with Fit for Duty being added to reflect the Canadian environment

## Slide 8: Proposed goal
To reduce slips, trips and fall incidents company-wide, by 20% per year. This translates to [Insert company # here] fewer people being hurt.
The proposed program aligns strategically:
Supporting the company core values, including increased commitment to safety, respect, raising the bar, honouring commitments and doing the right thing.
Continue to advance our journey to zero injuries and zero incidents.
Continue to advance a strong safety culture through:
  Working collaboratively to understand and manage slip, trip and fall hazards/risks
  Building capacity in our people and systems to operationalize the get a grip program

## Slide 9: Optimum program rollout schedule
Time Line |  | 
1. | Leadership engagement Identify level of effort Identify resources Order materials | Date TBD
2. | Awareness training for H&S, Comms and key stakeholders | Date TBD
3. | Program implementation | Date TBD
4. | Activity package 1 | Date TBD
5. | Activity package 2 | Date TBD
6. | Activity package 3 | Date TBD

## Slide 10: Preparing for Leadership engagement
Time Line |  | 
1. | Meeting with Energy Safety Canada | Date TBD
2. | Case for change presentation | Date TBD
3. | H&S check-in | Date TBD
4. | Functional area leadership team presentation | Date TBD
5. | Program final review & sign off by key H&S leaders | Date TBD
6. | Program implementation | Date TBD

## Slide 11: leadership alignment
Leadership Engagement
H&S works with leadership to assist with appropriate level of effort recommendation for their specific areas.
Functional area leadership team meetings
Budget secured
Functional Area Level of Effort Identification
Review draft level of effort and agree on upcoming years program
Functional Area Resource Allocation
Identify functional area sponsor and communicate expectations.
Identify functional area leaders.
Scheduled H&S to conduct orientation in partnership with the functional area leaders, sponsor(s), and/or champions.
Material Ordered
Identify material needs and order (https://escsafety.devcogroup.com/)
Distribute materials

## Slide 12: Initial questions for leadership
Consider:
How do you want to participate? To what degree?
Who will be the sponsor and the supporting leaders?
Do we have all the necessary departments or groups involved?
How will we measure success?

## Slide 13: Proposed Next steps: focused program
Activity Packages
Leaders use activity packages to help roll out the program.
Packages include Toolbox Talks, Inspections, Forms, etc.
Communications
H&S rolls out program on existing employee communication channels (i.e. internal website)
Communications could include: email, safety meetings, company website, social media (Twitter, Facebook etc.)

## Slide 14: Program implementation: Functional Area breakdown
Get a Grip Program Components | Smaller Location | Larger Location | Our Location
Case for change | ? hour(s) | ? hour(s) | ? hour(s)
Posters and tent cards | ? hour(s) | ? hour(s) | ? hour(s)
Activity package delivery | ? hour(s) | ? hour(s) | ? hour(s)
Activity package issue follow-up and Resolution | ? hour(s) | ? hour(s) | ? hour(s)
Hazard hunts | ? hour(s) | ? hour(s) | ? hour(s)
Hazard signage | ? hour(s) | ? hour(s) | ? hour(s)
Inspections | ? hour(s) | ? hour(s) | ? hour(s)
Total Hours | ? hour(s) | ? hour(s) | ? hour(s)

## Slide 15: Planning, design and release
Time Line |  | 
1. | Development of project execution plan | Date TBD
2. | Secure resources | Date TBD
3. | Informal lessons learned | Date TBD
4. | Project development work | Date TBD
5. | Minor tweaks and/or final deliverables | Date TBD
6. | Awareness training for H&S | Date TBD
7. | Program final review and sign off by functional area leaders | Date TBD
8. | Monitor and support roll out | Date TBD

## Slide 16: Roles and Responsibilities overview
H&S Team
Functional Area H&S Team
Functional Area Leadership Team and Sponsor
Functional Area Leaders
Ensure the Line of Fire program is maintained and improved yearly based on post-event lessons learned.
Act as a subject matter expert to support the functional area H&S team.
Provides a sample “starter kit” of materials to all functional area participating.
Hosts the campaign page on the company website and social media.
Co-host an orientation session in partnership with the functional area sponsor/s, H&S, communications specialist(s).
Work with functional areas to provide ongoing statistics and lessons learned.
Provide feedback on the program to Energy Safety Canada.
Review last year’s lessons learned and identify opportunities for improvement.
Conduct a review to draft upcoming years level of effort proposal.
Act as a local subject matter expert to support the functional area champions.
Provide program direction and works closely with functional area champion to prepare them to run the program.
Plan and schedule orientation session in partnership with the H&S team.
Provides ongoing statistical analysis of workplace injuries.
Provide feedback on the program to H&S team.
Review the draft level of effort and agree on upcoming years program.
Leadership team identifies functional area sponsor and communicates expectations.
Leadership team identifies functional area champion(s) and communicates expectations.
Provide ongoing stewardship of resource utilization, program success and challenges, associated work orders and/or corrective actions.
Work with H&S team to plan and schedule an orientation session in partnership with the H&S team.
Identify tactical material needs.
Lead roll out within their specific area.
Work with the function area sponsor to escalate issues or highlight opportunities.
Provide regular feedback to the functional area sponsor on progress.
Customize supporting campaign material
Work with the functional area team to act as an area subject matter expert.
Provide ongoing feedback on the program to functional area H&S team.
Notes: ESC to update